## Title Page
Group Number: 14
Group Name: Niner Transit Data
Group Members:
#1: Felipe Orrego
#2: Thien Nguyen
#3: Autumn Horrell
#4: Django Yepidan
#5: Jaren Robbins

## Product Backlog(To-do)
Group Number 14
Project Name: Niner Transit Data
Description: | Visualize, clean, train, and model data. | PRODUCT BACKLOG (TO-DO)
Team Members: | Felipe, Thien, Autumn, Django, Jaren
Story # | Card Front | Card Back | Sprint Number | Priority | Assigned To | Comments | Estimated Points | Estimated Hours | Estimated Velocity | Actual Velocity
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | Sprint 1 | [5 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours)
ST - 4 | As a developer, I would like to look at clean data (filtering out things such as stray zeroes) to make it easier to get more excellent results. | Pandas has many cleaning features that can do this cleaning for us. | Sprint 2 | 5th |  |  | 3 |  | #DIV/0! | #REF!
ST - 5 | As a student/driver, I would like to see more ways to tell what the activity looks like within the Niner Transit system. | The student should be able to see more graphs telling them critical information. | Sprint 2 | 4th |  |  | 5 |  | #DIV/0! | #REF!
ST - 6 | As a developer, I would like to create UML diagrams to map out the next steps of our project. | The developer should be able to create use cases and behavioral diagrams. | Sprint 2 | 11th |  |  | 3 |  | #DIV/0! | #REF!
ST - 7 | As a bus driver, I need the bus schedule to acknowledge the variation of passenger amounts so that the correct amount of busses will be used to avoid wasting time picking up no passengers. | Our app will calculate to provide variation of passenger amounts so the bus drivers will be able to avoid wasting time picking up no passengers. | Sprint 3 | 9th |  |  | 3 |  | #DIV/0! | #REF!
ST - 8 | As a UNCC student, I often feel that the busses are stopping way too often and creating traffic during busy hours. It takes me a long time to leave the school when there are more buses on the road. | Our app will notice when its peak hour on campus so the users will be able to avoid peak hour and our app will also notice and recommend the bus driver to manage to take alternative route to avoid traffic on campus during peak hours since during peak hours, buses shouldn't hold up traffic to the degree that they do now. | Sprint 3 | 10th |  |  | 8 |  | #DIV/0! | #REF!
ST - 9 | As a UNCC student, I want to be able to create an account with this app and be able to save my most used bus/route. | Our app will allow the users to create an account with our app. | Sprint 4 | 6th |  |  | 3 |  | #DIV/0! | #REF!
ST - 10 | As a UNCC student, I want my information is secured after creating an account with this transit app. | Our app will ensure that the user's information will be secured because privacy is our first priority. | Sprint 4 | 1st |  |  | 3 |  | #DIV/0! | #REF!
ST - 11 | As a UNCC student, I want this transit app to run smoothly without lagging or containing any bugs. | We will maintain and update our app regularly to make sure that our app always runs smoothly. | Sprint 4 | 8th |  |  | 1 |  | #DIV/0! | #REF!
ST - 12 | As a UNCC student, I want this transit app to be able to send me a notication noticing my bus is arrving or departing shortly. | Our app will be able to send the users notifications about their bus is arriving/departing. | Sprint 4 | 12th |  |  | 5 |  | #DIV/0! | #REF!

## DONE (post St.1 and St.2)
y | 14
Project Name: Niner Transit Data | UNCC Gaming Manager
Description: | Our software system will visualize, clean, train, and model data. The goal of our system is to visualize the data in different ways to learn more about the NIner Transit System and potential areas of improvement. Our software system will also include cleaning, training, and modeling data to better present potential solutions and optimizations.
Team Members | Felipe, Thien, Autumn, Django, Jaren
Note; This is an example of a "Done" page for Sprint 1 and Sprint 2 | [5 empty] | Sprint 1 |  |  |  | Sprint 2
Story # | Card Front | Card Back | Sprint Number | Priority* | Estimated Points | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Assigned To | Comments
| As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | [5 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours) |  |  | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours)
ST - 1 | As a developer, I would like to write out the problem and generate a response. | The developer should be able to create a plan on how to visualize and eventually optimize the Niner Transit data. | Sprint 1 | 7th | 1 | 0.5 | 0.5 | 2 | 2
ST - 2 | As a developer, I would like to visualize each Niner Transit route to get a better idea of the problem. | Each route can be visualized on the Passio GO! app or the University website. | Sprint 1 | 3rd | 1 | 1 | 0.5 | 1 | 2
ST - 3 | As a student/driver, I would like to visualize how many people get on and off each stop each year. | We can use pandas to manipulate the data and extract the specific values that we want. | Sprint 1 | 2nd | 3 | 2 | 1.5 | 1.5 | 2

## Doing
Group Number 14
Project Name: Niner Transit Data
Description: Visualize, clean, train, and model data. | DOING
Team Members: Felipe, Thien, Autumn, Django, Jaren
Story # | Card Front | Card Back | Estimated Points | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Sprint Number | Priority | Assigned To | Comments
ST - 1 | [5 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours) | Sprint 1
ST - 4 | As a developer, I would like to look at clean data (filtering out things such as stray zeroes) to make it easier to get more excellent results. | Pandas has many cleaning features that can do this cleaning for us. | 3 | 2 |  | 1.5 | #DIV/0! | Sprint 3 | 5th
ST - 5 | As a student/driver, I would like to see more ways to tell what the activity looks like within the Niner Transit system. | The student should be able to see more graphs telling them critical information. | 5 | 4 |  | 1.25 | #DIV/0! | Sprint 3 | 4th
ST - 6 | As a developer, I would like to create UML diagrams to map out the next steps of our project. | The developer should be able to create use cases and behavioral diagrams. | 3 | 2 |  | 1.5 | #DIV/0! | Sprint 3 | 11th
ST - 5
ST - 6
ST - 7
ST - 8
ST - 9
ST - 10
ST - 11
ST - 12

## Story Point Key
Story Point Key